## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 (Registeration) | 6
Taking student/ faculty details | 2 | Burhan | Completed | 2 | 1 | 1 | 5 | 0 | 1 | 0
Registering student/faculty on the system | 4 | Burhan | Completed | 4 | 0.5 | 0 | 3 | 0 | 0 | 0
User Story #2 (Float Course) | 20
Taking course name from faculty | 4 | Burhan | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0
Taking modules from the faculty | 6 | Burhan | Completed | 6 | 5 | 5 | 1 | 1 | 1 | 0
Taking outcomes for the modules | 6 | Burhan | Completed | 6 | 2 | 5 | 0 | 1 | 0 | 1
Recording modules and outcomes in the database | 4 | Burhan | Completed | 4 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 (Give Questions) | 24
Retrieving course | 4 | Burhan | Completed | 4 | 6 | 0 | 0 | 0 | 0 | 0
Retrive module | 4 | Burhan | Completed | 4 | 1 | 3 | 3 | 3 | 0 | 0
Retrieve outcome | 4 | Burhan | Completed | 4 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Give Questions | 12 | Burhan | Completed | 12 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 (Enroll Course) | 6
Selecting a course | 4 | Burhan | Completed | 4 | 4 | 2 | 2 | 1 | 1 | 0
Registering for the course | 2 | Burhan | Completed | 2 | 6 | 3 | 3 | 3 | 1 | 1
User Story #5 (Write Exam) | 12
Answer Questions | 8 | Burhan | Completed | 8 | 1 | 1 | 1 | 0.5 | 1 | 1
Give Feedback | 4 | Burhan | Completed | 4 | 6 | 6 | 0.5 | 3 | 9 | 0
Total |  |  |  | 68 | 41 | 37.5 | 24 | 14.5 | 15 | 7
Create a Sprint Backlog in Smartsheet